## Cockpit
A&O Repainting Report as per |  | 2024-09-20
|  |  | Project: | VISTA A&O. APEX REFACTORING OF VISTA TO APEX 23 | PAGES | DATE | PLANNED | NUMBERS | ACTUAL | TASKS | DATE | PLANNED | NUMBER | ACTUAL
Number of Pages: | 193 |  |  | - Vista A&O - Repainting | Start Repainting: | 2024-09-08 | 193 | 0 | 193 | Start Repainting: | 2024-09-08 | 1 | 0 | 1
[6 empty] | 2024-09-09 | 184 | 0 | 193 |  | 2024-09-09 | 1 | 0 | 1
Page Type Normal: | 148 |  |  |  |  | 2024-09-10 | 175 | 0 | 193 |  | 2024-09-10 | 1 | 0 | 1
Page Type Modal Dialog: | 45 |  | Documentation |  |  | 2024-09-11 | 166 | 0 | 193 |  | 2024-09-11 | 1 | 0 | 1
|  |  | Confluence: | Vista A&O Project |  | 2024-09-12 | 157 | 0 | 193 |  | 2024-09-12 | 1 | 0 | 1
Number of Pages Priority 1: | 193 |  | Jira Structure: | Vista A&O Jira Structure |  | 2024-09-13 | 148 | 0 | 193 |  | 2024-09-13 | 1 | 0 | 1
Number of Pages Priority 2: | 0 |  |  |  |  | 2024-09-14 | 139 | 0 | 193 |  | 2024-09-14 | 1 | 0 | 1
Number of Pages Priority 3: | 0 |  |  |  |  | 2024-09-15 | 130 | 0 | 193 |  | 2024-09-15 | 1 | 0 | 1
[6 empty] | 2024-09-16 | 121 | 0 | 193 |  | 2024-09-16 | 1 | 0 | 1
[6 empty] | 2024-09-17 | 112 | 0 | 193 |  | 2024-09-17 | 1 | 0 | 1
[6 empty] | 2024-09-18 | 103 | 0 | 193 |  | 2024-09-18 | 1 | 0 | 1
[6 empty] | 2024-09-19 | 94 | 0 | 193 |  | 2024-09-19 | 1 | 0 | 1
[6 empty] | 2024-09-20 | 85 | 0 | 193 |  | 2024-09-20 | 1 | 0 | 1
[6 empty] | 2024-09-21 | 76 | 0 | 193 |  | 2024-09-21 | 1 | 0 | 1
[6 empty] | 2024-09-22 | 67 | 0 | 193 |  | 2024-09-22 | 1 | 0 | 1
[6 empty] | 2024-09-23 | 58 | 0 | 193 |  | 2024-09-23 | 1 | 0 | 1
Number of Page Status OPEN: | 193 |  |  |  |  | 2024-09-24 | 49 | 0 | 193 |  | 2024-09-24 | 1 | 0 | 1
Number of Page Status IN PROGRESS: | 0 |  |  |  |  | 2024-09-25 | 40 | 0 | 193 |  | 2024-09-25 | 1 | 0 | 1
Number of Page Status TESTABLE: | 0 |  |  |  |  | 2024-09-26 | 31 | 0 | 193 |  | 2024-09-26 | 1 | 0 | 1
Number of Page Status TEST OK: | 0 |  |  |  |  | 2024-09-27 | 22 | 0 | 193 |  | 2024-09-27 | 1 | 0 | 1
[6 empty] | 2024-09-28 | 13 | 0 | 193 |  | 2024-09-28 | 1 | 0 | 1
[6 empty] | 2024-09-29 | 4 | 0 | 193 |  | 2024-09-29 | 1 | 0 | 1
[5 empty] | Ende Repainting | 2024-09-30 | 0 | 0 | 193 | Ende Repainting | 2024-09-30 | 0 | 0 | 1
Number of Tasks: | 1
Number of Tasks Status OPEN: | 1
Number of Tasks Status IN PROGRESS: | 0
Number of Tasks Status TESTABLE: | 0
Number of Tasks Status TEST OK: | 0
Formulas:
DATE = [DATE, row above]+1

## Page raw
ID | PAGE_ID | PAGE_NAME | PAGE_MODE | STATUS | PRIORITY | START_DATE | FINISH_DATE
115 | 9130 | SEC_PI_DYN_ACTUATE_APEX_VW_LIST | Normal | OPEN | 1
116 | 9132 | SEC_PAGE_DYN_AFFECT_APEX_VW_LIST | Normal | OPEN | 1
117 | 9134 | SEC_ITEM_DYN_AFFECT_APEX_VW_LIST | Normal | OPEN | 1
118 | 9136 | SEC_DYN_SCREEN_APEX_VW_LIST | Normal | OPEN | 1
119 | 9138 | SEC_DYN_FIELD_APEX_VW_LIST | Normal | OPEN | 1
120 | 9140 | SEC_APP_MENU_DEF_APEX_VW_LIST | Normal | OPEN | 1
121 | 9150 | SEC_RUNNING_MAN_DEF_APEX_VW_LIST | Normal | OPEN | 1
122 | 9152 | SEC_RUNNING_MAN_DYN_APEX_VW_LIST | Normal | OPEN | 1
123 | 9999 | Login Page | Normal | OPEN | 1
124 | 10208 | DMS_DROPZONE_CHILD_SHPT_VW_LIST | Normal | OPEN | 1
125 | 13506 | VCO_APPLICATION_MENU_VW_LIST | Normal | OPEN | 1
126 | 13518 | VCO_APPLICATION_PAGES_VW_LIST | Normal | OPEN | 1
127 | 13520 | VCO_RUNNING_MAN_VW_LIST | Normal | OPEN | 1
128 | 13522 | VCO_RUNNING_MAN_PARAM_LIST | Normal | OPEN | 1
129 | 10001 | Change Password | Normal | OPEN | 1
130 | 14001 | RNT_ORDERTAB_DML | Normal | OPEN | 1
131 | 15216 | CTM_CUSTOMS_LIST | Normal | OPEN | 1
132 | 30019 | ASSIGNIBC.RPT | Modal Dialog | OPEN | 1
133 | 30027 | AUTOMATCH_ITI.RPT | Modal Dialog | OPEN | 1
134 | 30033 | BOOK_CODA_INVOICE_LINES.RPT | Modal Dialog | OPEN | 1
135 | 30034 | BOOK_CR_ON_INC_INV.RPT | Modal Dialog | OPEN | 1
136 | 30051 | CANCEL_ITI.RPT | Modal Dialog | OPEN | 1
137 | 30052 | CANCEL_OUTTAKELINE.RPT | Modal Dialog | OPEN | 1
138 | 30064 | CHANGEORDERINVOICETO.RPT | Modal Dialog | OPEN | 1
139 | 30089 | CLOSE.RPT | Modal Dialog | OPEN | 1
140 | 30135 | COPY_EQ_TRANSACTION.RPT | Modal Dialog | OPEN | 1
141 | 30164 | CX_AUSFUHRBESCHEINIGUNG.RPT | Modal Dialog | OPEN | 1
142 | 30174 | CX_CLEANINGCERTIFICATE.RPT | Modal Dialog | OPEN | 1
143 | 30290 | DEPOTOUT.RPT | Modal Dialog | OPEN | 1
144 | 30326 | EXECUTEIBCDELIVERY.RPT | Modal Dialog | OPEN | 1
145 | 30342 | FINDQUOTATION.RPT | Modal Dialog | OPEN | 1
146 | 30357 | GENQUOTEFROMORDER.RPT | Modal Dialog | OPEN | 1
147 | 30359 | GENQUOTPRODSTOPS.RPT | Modal Dialog | OPEN | 1
148 | 30360 | GENQUOTROUTES.RPT | Modal Dialog | OPEN | 1
149 | 30401 | INSADRES.RPT | Modal Dialog | OPEN | 1
150 | 30445 | MASTER_ORDER_FROM_ORDER.RPT | Modal Dialog | OPEN | 1
151 | 30474 | PERFORMANCE_REASON.RPT | Modal Dialog | OPEN | 1
152 | 30475 | PLANONEIBC.RPT | Modal Dialog | OPEN | 1
153 | 30487 | PROCESSORDER | Modal Dialog | OPEN | 1
154 | 30547 | ROLLBACKEXECUTEIBCDELIVERY.RPT | Modal Dialog | OPEN | 1
155 | 30551 | ROLLBACKORDER.RPT | Modal Dialog | OPEN | 1
156 | 30590 | SHOWMATCHQUOTE.RPT | Modal Dialog | OPEN | 1
157 | 30604 | TODO_DONE.RPT | Modal Dialog | OPEN | 1
158 | 30699 | CLOSE_INTERMODAL_COST.RPT | Modal Dialog | OPEN | 1
159 | 30769 | UNMATCH_INC_INVL.RPT | Modal Dialog | OPEN | 1
160 | 30770 | BOOK_MR_CR_ON_INC_INV.RPT | Modal Dialog | OPEN | 1
161 | 30775 | REDETERMINE_CUST_SERV_REP.RPT | Modal Dialog | OPEN | 1
162 | 30781 | REM_REV_FROM_ITI_DETAIL.RPT | Modal Dialog | OPEN | 1
163 | 30782 | MATCH_REV_TO_ITI_DETAILS.RPT | Modal Dialog | OPEN | 1
164 | 30830 | BOOK_CR_ON_INC_INV.RPT | Modal Dialog | OPEN | 1
165 | 30852 | DELETE_ITI_HEADER.RPT | Modal Dialog | OPEN | 1
166 | 30862 | CHANGE_REMOVE_DEBTOR_NUMBER.RPT | Modal Dialog | OPEN | 1
167 | 41002 | DMS_DOC_ARCHIVED_VW_LIST | Normal | OPEN | 1
168 | 3087 | EQUIPMENT_TKCTAB_DML | Normal | OPEN | 1
169 | 30610 | UNASSIGNIBC_IBC.RPT | Modal Dialog | OPEN | 1
170 | 30611 | UNASSIGNIBC_OET.RPT | Modal Dialog | OPEN | 1
171 | 30615 | UPDATECMRFLAG.RPT | Modal Dialog | OPEN | 1
172 | 30644 | CX_EXTRA_COST_NOTIFICATION.RPT | Modal Dialog | OPEN | 1
173 | 30698 | CLOSE_INTERMODAL.RPT | Modal Dialog | OPEN | 1
174 | 14003 | RNT_SHIPMENT_VWTAB_DML | Normal | OPEN | 1
175 | 2503 | WORKSHOP_AGREEMENT_DEBTOR_OFFTAB_DML | Normal | OPEN | 1
176 | 2299 | INV_COST_CODE_VWTAB_DML | Normal | OPEN | 1
177 | 4973 | V_EQUIP_COMP_TRUTAB_DML | Normal | OPEN | 1
178 | 2309 | COST_CODE_RENTTAB_DML | Normal | OPEN | 1
179 | 3877 | OTHERTAB_DML | Normal | OPEN | 1
180 | 5003 | V_EQUIP_SETT_TKCTAB_DML | Normal | OPEN | 1
181 | 5025 | V_EQ_TYPE_CHASSISTAB_DML | Normal | OPEN | 1
182 | 4127 | QUOTATION_AUX_EQUIP1TAB_DML | Normal | OPEN | 1
183 | 8837 | ADA_TERMS_COND_LIB_DML | Normal | OPEN | 1
184 | 2987 | EMPLOYEETAB_DML | Normal | OPEN | 1
185 | 5903 | V_SUB_GUTSCHRIFT_APEXTAB_DML | Normal | OPEN | 1
186 | 2275 | CONTAINERTAB_DML | Normal | OPEN | 1
187 | 6201 | ACTION_NEWTAB_DML | Normal | OPEN | 1
188 | 30548 | ROLLBACKEXECUTEIBCORDER.RPT | Modal Dialog | OPEN | 1
189 | 30327 | EXECUTEIBCORDER.RPT | Modal Dialog | OPEN | 1
190 | 8842 | ADA_TERMS_COND_LIST | Normal | OPEN | 1
191 | 4693 | TODOTAB_DML | Normal | OPEN | 1
192 | 8836 | ADA_TERMS_COND_LIB_LIST | Normal | OPEN | 1
193 | 41000 | DMS_Drop_Zone | Normal | OPEN | 1
24 | 2014 | CF_BILLING_METHOD_VW_LIST | Normal | OPEN | 1
25 | 2015 | CF_BILLING_METHOD_VWTAB_DML | Normal | OPEN | 1
26 | 2072 | COMPANY_LIST | Normal | OPEN | 1
27 | 2076 | COMPANY_FINANCIALS_LIST | Normal | OPEN | 1
28 | 2077 | COMPANY_FINANCIALSTAB_DML | Normal | OPEN | 1
29 | 2280 | COM_CFBM_COMPANY_TYPE_LIST | Normal | OPEN | 1
30 | 2384 | ACTION_TKC_EQ_LIST | Normal | OPEN | 1
31 | 2488 | AGENDA_TKC_EQ_LIST | Normal | OPEN | 1
32 | 2860 | EDI_EXT_ORD_UNI_VWTAB_LIST | Normal | OPEN | 1
33 | 2864 | EDI_EXT_ORD_UNI_VW_3_LIST | Normal | OPEN | 1
34 | 2906 | EDI_ORDER2_LIST | Normal | OPEN | 1
35 | 2907 | EDI_ORDER2TAB_DML | Normal | OPEN | 1
36 | 3030 | COM_CFR_HAZARD_DATA_GRPS_LIST | Normal | OPEN | 1
37 | 3086 | EQUIPMENT_TKC_LIST | Normal | OPEN | 1
38 | 3348 | EXE_EVENT_V_EQ_TKC_LIST | Normal | OPEN | 1
39 | 3630 | ITI_DETAILS_LIST | Normal | OPEN | 1
40 | 3632 | ITI_HEADER_LIST | Normal | OPEN | 1
41 | 3810 | MODULE_LIST | Normal | OPEN | 1
42 | 3858 | ORDER_ADMIN_EVT_EXE_LIST | Normal | OPEN | 1
43 | 3872 | ORDER_STOP_LIST | Normal | OPEN | 1
44 | 4000 | PRODUCT_CODE_LIST | Normal | OPEN | 1
45 | 4122 | QUOTATION_ACTION_LIST | Normal | OPEN | 1
46 | 4124 | QUOTATION_AUX_EQUIP_LIST | Normal | OPEN | 1
47 | 4126 | QUOTATION_AUX_EQUIP1_LIST | Normal | OPEN | 1
48 | 4140 | QUOTATION_INTERVAL_LIST | Normal | OPEN | 1
49 | 4144 | QUOTATION_PRODUCT_LIST | Normal | OPEN | 1
50 | 4148 | QUOTATION_ROUTING_LIST | Normal | OPEN | 1
51 | 4240 | V_EQUIP_COMMDEV_TKC_LIST | Normal | OPEN | 1
52 | 4250 | V_EQUIP_COMP_TKC_LIST | Normal | OPEN | 1
53 | 4423 | SHIPMENT_PRODUCTSTOPTAB_DML | Normal | OPEN | 1
54 | 4428 | SHIP_ADMIN_EVT_EXE_LIST | Normal | OPEN | 1
55 | 4430 | SHIP_CLOSURE_EXE_LIST | Normal | OPEN | 1
56 | 4640 | TMS_DEM_LINES_CST_VW_LIST | Normal | OPEN | 1
57 | 4646 | TMS_DEM_LINES_SBC_VW_LIST | Normal | OPEN | 1
58 | 4692 | TODO_LIST | Normal | OPEN | 1
59 | 4844 | V_ADDITIONAL_REVENUE_LIST | Normal | OPEN | 1
60 | 4940 | V_CR_SHIPMENT_LIST | Normal | OPEN | 1
61 | 4954 | V_DEPOT_CONST_TKC_LIST | Normal | OPEN | 1
62 | 4955 | V_DEPOT_CONST_TKCTAB_DML | Normal | OPEN | 1
63 | 4978 | V_EQUIP_DATES_TKC_LIST | Normal | OPEN | 1
64 | 4992 | V_EQUIP_PUMP_TKC_LIST | Normal | OPEN | 1
65 | 5002 | V_EQUIP_SETT_TKC_LIST | Normal | OPEN | 1
66 | 5010 | V_EQUIP_TUBE_TKC_LIST | Normal | OPEN | 1
67 | 5206 | V_QUOTATION_REQUEST_LIST | Normal | OPEN | 1
68 | 5207 | V_QUOTATION_REQUESTTAB_DML | Normal | OPEN | 1
69 | 5208 | V_QUOTE_ROUTE_STOP2_LIST | Normal | OPEN | 1
93 | 8766 | EQUIPMENT_RENTAL_TYPE_LIST | Normal | OPEN | 1
94 | 8830 | ADA_RENTAL_ORDER_VW_LIST | Normal | OPEN | 1
95 | 8831 | ORDER_MASTERTAB_DML | Normal | OPEN | 1
96 | 8832 | ADA_OMA_RENTAL_REQUEST_LIST | Normal | OPEN | 1
97 | 6300 | INV_JJ_CLOSURE_RESULT_LIST | Normal | OPEN | 1
98 | 6400 | INV_SHIP_CLOS_RESULT_COST_VW_LIST | Normal | OPEN | 1
99 | 6402 | INV_SHIP_CLOS_RESULT_REV_VW_LIST | Normal | OPEN | 1
100 | 6205 | TMS_ORDERS_MKT_APEX_VWTAB_DML | Normal | OPEN | 1
101 | 8834 | ADA_OMA_RENTAL_REQUEST_LINE_LIST | Normal | OPEN | 1
102 | 8839 | ADA_RENTAL_CONTRACT_DML | Normal | OPEN | 1
103 | 8864 | ADA_ORDER_RENTAL_RESOURCE_VW_LIST | Normal | OPEN | 1
104 | 8866 | On/Off Hire | Normal | OPEN | 1
105 | 8833 | ADA_OMA_RENTAL_REQUESTTAB_DML | Normal | OPEN | 1
106 | 8899 | ADA_REQUEST_LINES_VWTAB_DML | Normal | OPEN | 1
107 | 8960 | EDI_ESTIMATE_INTRAY_LIST | Normal | OPEN | 1
108 | 8971 | ADA_ERENT_ADD_CR_DML_VW_DML | Normal | OPEN | 1
109 | 9100 | SEC_MAIN_GROUP_LIST | Normal | OPEN | 1
110 | 9102 | SEC_APP_USER_APEX_VW_LIST | Normal | OPEN | 1
111 | 9104 | SEC_MGRP_SGRP_APEX_VW_LIST | Normal | OPEN | 1
112 | 9106 | SEC_SECURITY_GROUP_LIST | Normal | OPEN | 1
113 | 9110 | SEC_PAGE_DEF_APEX_VW_LIST | Normal | OPEN | 1
114 | 9120 | SEC_PAGE_ITEM_DEF_APEX_VW_LIST | Normal | OPEN | 1
70 | 5268 | TMS_SHIPMENT_DETAILS3_APEX_LIST | Normal | OPEN | 1
71 | 5280 | V_SUBSTAT_HIST_TKC_LIST | Normal | OPEN | 1
72 | 5526 | EQ_EQUIPMENT_DEVICES_LIST | Normal | OPEN | 1
73 | 5580 | INV_CFBM_CHANGES_LIST | Normal | OPEN | 1
74 | 5802 | SHE_INCIDENTS_LIST | Normal | OPEN | 1
75 | 5926 | MATCHBOARD_APEX_LIST | Normal | OPEN | 1
76 | 6200 | ACTION_NEW_LIST | Normal | OPEN | 1
77 | 6202 | TMS_SHIPMENTS_MKT_APEX_VW_LIST | Normal | OPEN | 1
78 | 6204 | TMS_ORDERS_MKT_APEX_VW_LIST | Normal | OPEN | 1
79 | 7450 | CONTRACT_TRUCKING_LIST | Normal | OPEN | 1
80 | 7452 | AGREEMENT_LIST | Normal | OPEN | 1
81 | 7454 | AGREEMENT_ACTIVITY_LIST | Normal | OPEN | 1
82 | 7456 | AGREEMENT_VALIDITY_LIST | Normal | OPEN | 1
83 | 7466 | ADA_AGREEMENT_SUR_VW_LIST | Normal | OPEN | 1
84 | 7468 | ADA_CONTRACT_SUR_VW_LIST | Normal | OPEN | 1
85 | 7470 | ADA_RELATION_SUR_VW_LIST | Normal | OPEN | 1
86 | 7474 | MATRIX_AGREEMENT_LIST | Normal | OPEN | 1
87 | 7486 | QTN_QUOTE_ROUTE_SECTIONS_LIST | Normal | OPEN | 1
88 | 8610 | REPAIR_CODE_LIST | Normal | OPEN | 1
89 | 8700 | ORDER_MASTER_LIST | Normal | OPEN | 1
90 | 8701 | ADA_ORDER_ESTIMATE_VW_DML | Normal | OPEN | 1
91 | 8744 | ADA_COST_REV_VW_LIST | Normal | OPEN | 1
92 | 8746 | ADA_COST_REV_VW_LIST | Normal | OPEN | 1
1 | 4913 | V_CR_IBC_ORDER_PERTAB_DML | Normal | OPEN | 1
2 | 2103 | COM_ADDR_HNDL_EQM_TRTAB_DML | Normal | OPEN | 1
3 | 4023 | PRODUCT_OVERVIEWTAB_DML | Normal | OPEN | 1
4 | 6203 | TMS_SHIPMENTS_MKT_APEX_VWTAB_DML | Normal | OPEN | 1
5 | 4845 | V_ADDITIONAL_REVENUETAB_DML | Normal | OPEN | 1
6 | 4123 | QUOTATION_ACTIONTAB_DML | Normal | OPEN | 1
7 | 1125 | TMS_FUNCTION_TYPESTAB_DML | Normal | OPEN | 1
8 | 9918 | IBC_OVERVIEW | Normal | OPEN | 1
9 | 8843 | ADA_TERMS_COND_DML | Normal | OPEN | 1
10 | 10000 | Forgot Password | Normal | OPEN | 1
11 | 1 | Home | Normal | OPEN | 1
12 | 2 | Hoyer Vista Home dashboard | Normal | OPEN | 1
13 | 101 | Login Page | Normal | OPEN | 1
14 | 104 | Change Password | Normal | OPEN | 1
15 | 105 | Forgot Password | Normal | OPEN | 1
16 | 200 | TEST AW | Normal | OPEN | 1
17 | 204 | CrystalViewer | Modal Dialog | OPEN | 1
18 | 205 | FileViewer | Modal Dialog | OPEN | 1
19 | 210 | Viewer | Modal Dialog | OPEN | 1
20 | 1080 | EQ_EQUIPMENT_QUALIFICATIONS_LIST | Normal | OPEN | 1
21 | 1082 | TMS_SHIPMENT_REQUIRED_QUALI_VW_LIST | Normal | OPEN | 1
22 | 0 | Global Page | Normal | OPEN | 1
23 | 1202 | OTD_PLANNING_CLUSTER_LIST | Normal | OPEN | 1

## Task raw
ID | PAGE_ID | STATUS | PRIORITY | START_DATE | FINISH_DATE | DESCRIPTION | CLUSTER_NAME | DEVELOPER | TESTER
1 | 4913 | OPEN | 1 |  |  |  | HOYER Logo oben rechts | ALI CEYHAN | MATTHIAS ROM